## Comparison 5-12-22
2022-05-12
# | Scope of Work | 2022-11-05 | 2022-05-12 | Difference
1 | Pre-Application Meeting | 0 | 0 | 0
2 | Development Permit Fee | 0 | 0 | 0
3 | Development Permit - Grading Fee | 0 | 0 | 0
4 | Sanitary Sewer Trunk Fund | 0 | 0 | 0
5 | Building Permit Fee | 0 | 0 | 0
6 | Wrap Up Insurance / Builders Risk | 166366 | 183431 | 17065
7 | General Requirements | 1976772 | 2005629 | 28857
8 | Alberta New Home Warranty Rental Exemption | 695 | 695 | 0
9 | Design & Development (M/E/S/C/L) | 0 | 0 | 0
10 | GeoTech / Survey / Flow Test | 4500 | 4500 | 0
11 | Demolition / Hydrovac / Tree Hoarding | 20502 | 20502 | 0
12 | Earthwork | 549816 | 560720 | 10904
13 | PC SUM - Balcony Screw Piles | 59801 | 65946 | 6145
14 | Foundation Piles | 598182 | 603182 | 5000
15 | Asphalt Paving - Parking Lot | 129867 | 143543 | 13676
17 | PC SUM - Site Concrete | 257026 | 257026 | 0
18 | Misc. Site Concrete | 239234 | 259232 | 19998
19 | PC SUM - Ornamental Fencing | 63000 | 66823 | 3823
20 | PC SUM - Chain Link Fencing (Storage Units) | 67500 | 76646 | 9146
21 | PC SUM - Landscaping, Landscape Repair & Irrigation | 259404 | 262836 | 3432
22 | Foundations & Slabs | 3394563 | 4377836 | 983273
23 | Bonding - Formwork | 9296 | 16253 | 6957
24 | Bonding - Reinforcing Steel | 6347 | 7378 | 1031
25 | PC SUM - Parkade Mud Slab | 45049 | 47447 | 2398
26 | PC SUM - Masonry | 245518 | 292003 | 46485
27 | PC SUM - Structural & Misc. Steel | 1112497 | 1195397 | 82900
28 | Misc Steel Install | 9555 | 9555 | 0
29 | PC SUM - Carpentry Supply | 109007 | 161363 | 52356
30 | Carpentry Install | 141134 | 141134 | 0
31 | PC SUM - Kitchen & Bathroom Cabinets | 965500 | 1012525 | 47025
32 | PC SUM - Common Area Millwork | 110300 | 110300 | 0
33 | PC SUM - Wood Doors & Trims Supply | 209897 | 259215 | 49318
34 | Suite Doors & Trim Distribution | 4824 | 4824 | 0
35 | PC SUM - Railing Supply | 74092 | 85146 | 11054
36 | Millwork Install | 214860 | 227071 | 12211
37 | Insulation & Foundation Treatment | 237151 | 249846 | 12695
38 | Spray Foam Insulation | 25000 | 25000 | 0
39 | Fire Stopping / Fire Spray | 171987 | 190614 | 18627
40 | PC SUM - Fire Spray 4th Floor Corridors | 25000 | 25000 | 0
41 | PC SUM - Vinyl Decking & Aluminum Railings | 206697 | 232240 | 25543
42 | Hardie Board & Lux Siding | 2178744 | 2636799 | 458055
43 | Bonding - Siding | 21787 | 42188 | 20401
44 | PC SUM - SBS Roof | 1000977 | 1034016 | 33039
45 | PC SUM - Bonding - Roofing | 13863 | 12150 | -1713
46 | Flashings / Caulking / Peel and Stick | 84692 | 88463 | 3771
47 | FRP Panel | 13769 | 15177 | 1408
48 | PC SUM - HMD / PSF Supply | 80347 | 112425 | 32078
49 | HMD & PSF Install | 29870 | 29870 | 0
50 | PC SUM - Finish Hardware | 251500 | 286995 | 35495
51 | PC SUM - Card Access System | 42600 | 42600 | 0
52 | PC SUM - Filter Access Doors Supply | 20200 | 20503 | 303
53 | Filter Access Install | 9474 | 9474 | 0
54 | PC SUM - Aluminum Doors & Windows | 315234 | 417750 | 102516
55 | PC SUM - PVC Windows | 423691 | 492207 | 68516
56 | PC SUM - Overhead Door | 9975 | 13572 | 3597
57 | Parging | 26400 | 28500 | 2100
58 | PC SUM - Structural stud / deck / insulation / vapour barrier / tape | 7896670 | 8968070 | 1071400
59 | PC SUM - Architectural Ceilings | 250000 | 250000 | 0
60 | Bonding - Steel Studs & Drywall | 70046 | 76228 | 6182
61 | PC SUM - Flooring | 641495 | 669925 | 28430
62 | PC SUM - Floor Patch | 20000 | 22000 | 2000
63 | Bonding - Flooring | 7610 | 8341 | 731
64 | Painting | 359489 | 386795 | 27306
65 | PC SUM - Partitions / Lockers / Corner Guards | 23952 | 26418 | 2466
66 | Partitions / Lockers / Corner Guards Install | 7622 | 7622 | 0
67 | PC SUM - Postal | 10984 | 12082 | 1098
68 | Postal Install | 2251 | 2251 | 0
69 | PC SUM - Washroom Accessories Supply | 29360 | 31570 | 2210
70 | Washroom Accessories Install | 17810 | 17810 | 0
71 | PC SUM - Commercial Laundry Equipment | 23381 | 23381 | 0
72 | PC SUM - Appliances | 453662 | 497404 | 43742
73 | PC SUM - Wire shelving / Mirrors to suites | 35045 | 35045 | 0
74 | Elevators | 468102 | 453130 | -14972
75 | Site Servicing | 278952 | 348600 | 69648
76 | Mechanical | 4568612 | 4399920 | -168692
77 | Bonding - Mechanical | 38515 | 37079 | -1436
78 | Corridor Pressurization units | 345400 | 390000 | 44600
79 | Sprinklers | 306000 | 313000 | 7000
80 | Electrical | 1919783 | 2375836 | 456053
81 | Bonding - Electrical | 24640 | 28727 | 4087
82 | PC SUM - Connect from Demark to P/L | 15000 | 15000 | 0
83 | PC Sum Lighting Package | 152809 | 152809 | 0
84 | Misc. Freight | 2000 | 2000 | 0
85 | PC SUM - Fireplace | 25000 | 25000 | 0
86 | P.C Sum - Winter Conditions | 300000 | 300000 | 0
87 | P.C Sum - Testing & Inspections | 125000 | 125000 | 0
88 | P.C Sum - Printing Fees | 15000 | 15000 | 0
89 | PC SUM - Natural Gas Connection | 20000 | 20000 | 0
| Sub-Total | 34688252 | 38499590 | 3811338
90 | Overhead & Fee (6%) | 2081209 | 2309975 | 228766
91 | Total | 36769461 | 40809565 | 4040104
Emmanuel Home Expenses
# | Scope of Work | 2021-04-30 | 2022-05-12 | Difference
Design Development Fees
1 | Coromed & Dickson Management Fee | 79886 | 79886 | 0
2 | Dub Architecture | 500000 | 500000 | 0
3 | Ethos Engineering | 114690 | 114690 | 0
4 | Wasnea Engineering | 75440 | 75440 | 0
5 | ECCOM Engineering | 48500 | 48500 | 0
6 | Grade Engineering | 18000 | 18000 | 0
7 | Design North | 12000 | 12000 | 0
8 | Shelby Engineering | 9095 | 9095 | 0
9 | Pals Geomatics | 3000 | 3000 | 0
10 | Interior Design (Budget) | 0 | 30000 | 30000
City Expenses
11 | Pre-Application Meeting | 337 | 337 | 0
12 | Development Permit Fee | 8025 | 8025 | 0
13 | Development Permit - Grading Fee | 1608 | 1608 | 0
14 | Sanitary Sewer Trunk Fund | 125846 | 127159 | 1313
15 | Building Permit Fee | 309850 | 310131 | 281
16 | B.G.N Municipal Upgrades | 161400 | 161400 | 0
17 | Sanitary / Storm / Water Connection Fee - Undetermined | 125000 | 125000 | 0
Developer Expenses (Dub)
18 | Asbestos Pipe Removal | 12500 | 12500 | 0
19 | Concrete Tunnel Removal | 45000 | 45000 | 0
20 | Future Roadway Construction | 84788 | 84788 | 0
21 | Waterline & Hydrant Upgrades - Undetermined | $ | $
Furniture / Fixtures / Equipment
22 | Landscape Furniture (Park Benches / Tables / Chairs) | 127940 | 127940 | 0
23 | Treated Landscape Boxes | 60083 | 60083 | 0
24 | Security & Fire Alarm | 49600 | 49600 | 0
| Cost Saving Options | Projected Savings
1 | Change screw piles to cast in place. | 10000
2 | Eliminate or reduce amount of fence around property. | 65000
3 | Reduce amount of brick on the exterior of the building. | 85000
4 | Purchase misc lumber package when prices drop. | 50000
5 | Purchase interior finishing package when / if prices drop. | 25000
6 | Alternate decking materials. | 15000
7 | Use alternate exterior finish products. | 1000000
8 | Use fiberglass windows in place of aluminum. | 50000
9 | Use white window in place of black. | 45000
10 | Review and discuss options with Kerr / KDH. | 300000
11 | Review and discuss cost saving options with Canwest. | 25000
12 | Muth? | 150000
| Total | 1820000