## Sheet1
|  | Budget |  |  |  | Costs
|  | Original | Changes |  | Current | Total in Place |  | Previous | Current | Estimate to Complete
| Detailed Budget Breakdown | $ | $ | % | $ | $ | % | $ | $ | $ | %
General Conditions
1 | Pre-Application Meeting | 0 |  | 0% | 0 | 0 | 0% |  |  | 0 | #DIV/0!
2 | Development Permit Fee | 0 |  | 0% | 0 | 0 | 0% |  |  | 0 | #DIV/0!
3 | Development Permit - Grading Fee | 0 |  | 0% | 0 | 0 | 0% |  |  | 0 | #DIV/0!
4 | Sanitary Sewer Trunk Fund | 0 |  | 0% | 0 | 0 | 0% |  |  | 0 | #DIV/0!
5 | Building Permit Fee | 0 |  | 0% | 0 | 0 | 0% |  |  | 0 | #DIV/0!
6 | Wrap Up Insurance / Builders Risk | 166366 |  | 0% | 166366 | 0 | 0% |  |  | 166366 | 100%
7 | General Requirements | 1976772 |  | 0% | 1976772 | 0 | 0% |  |  | 1976772 | 100%
8 | Alberta New Home Warranty Rental Exemption | 695 |  | 0% | 695 | 0 | 0% |  |  | 695 | 100%
9 | Design & Development (M/E/S/C/L) | 0 |  | 0% | 0 | 0 | 0% |  |  | 0 | #DIV/0!
10 | Real Property Report & GeoTech Evaluation | 4500 |  | 0% | 4500 | 0 | 0% |  |  | 4500 | 100%
84 | Misc. Freight | 2000 |  | 0% | 2000 | 0 | 0% |  |  | 2000 | 100%
86 | PC Sum - Winter Conditions | 300000 |  | 0% | 300000 | 0 | 0% |  |  | 300000 | 100%
87 | PC Sum - Testing & Inspections | 125000 |  | 0% | 125000 | 0 | 0% |  |  | 125000 | 100%
88 | PC Sum - Printing Fees | 15000 |  | 0% | 15000 | 0 | 0% |  |  | 15000 | 100%
89 | PC Sum - Natural Gas Connection | 20000 |  | 0% | 20000 | 0 | 0% |  |  | 20000 | 100%
| General Conditions - Totals | 2610333 | 0 | 0% | 2610333 | 0 | 0% | 0 | 0 | 2610333 | 100%
Sitework
11 | Demolition / Hydrovac / Tree Hoarding | 20502 |  | 0% | 20502 | 0 | 0% |  |  | 20502 | 100%
12 | Earthwork | 549816 |  | 0% | 549816 | 0 | 0% |  |  | 549816 | 100%
13 | Balcony Screw Piles | 59801 |  | 0% | 59801 | 0 | 0% |  |  | 59801 | 100%
14 | Foundation Piles | 598182 |  | 0% | 598182 | 0 | 0% |  |  | 598182 | 100%
15 | Asphalt Paving - Parking Lot | 129867 |  | 0% | 129867 | 0 | 0% |  |  | 129867 | 100%
17 | PC SUM - Site Concrete | 257026 |  | 0% | 257026 | 0 | 0% |  |  | 257026 | 100%
18 | Misc. Site Concrete | 239234 |  | 0% | 239234
19 | Ornamental Fencing | 63000 |  | 0% | 63000 | 0 | 0% |  |  | 63000 | 100%
20 | Chain Link Fencing (Storage Units) | 67500 |  | 0% | 67500 | 0 | 0% |  |  | 67500 | 100%
21 | PC SUM - Landscaping, Landscape Repair & Irrigation | 259404 |  | 0% | 259404 | 0 | 0% |  |  | 259404 | 100%
75 | Site Servicing | 278952 |  | 0% | 278952 | 0 | 0% |  |  | 278952 | 100%
| Sitework - Totals | 2523284 | 0 | 0% | 2523284 | 0 | 0% | 0 | 0 | 2284050 | 90.52%
Building Construction Costs
22 | Foundations & Slabs | 3394563 |  | 0% | 3394563 | 0 | 0% |  |  | 3394563 | 100%
23 | Bonding - Formwork | 9296 |  | 0% | 9296 | 0 | 0% |  |  | 9296 | 100%
24 | Bonding - Reinforcing Steel | 6347 |  | 0% | 6347 | 0 | 0% |  |  | 6347 | 100%
25 | PC SUM - Parkade Mud Slab | 45049 |  | 0% | 45049 | 0 | 0% |  |  | 45049 | 100%
26 | PC SUM - Masonry | 245518 |  | 0% | 245518 | 0 | 0% |  |  | 245518 | 100%
27 | PC SUM - Structural & Misc Steel | 1112497 |  | 0% | 1112497 | 0 | 0% |  |  | 1112497 | 100%
28 | Misc Steel Install | 9555 |  | 0% | 9555
29 | Carpentry Supply | 109007 |  | 0% | 109007 | 0 | 0% |  |  | 109007 | 100%
30 | Carpentry Install | 141134 |  | 0% | 141134
31 | PC SUM - Suite Cabinets | 965500 |  | 0% | 965500 | 0 | 0% |  |  | 965500 | 100%
32 | Common Area Millwork | 110300 |  | 0% | 110300 | 0 | 0% |  |  | 110300 | 100%
33 | PC SUM - Wood Doors & Trims Supply | 209897 |  | 0% | 209897 | 0 | 0% |  |  | 209897 | 100%
34 | Suite Doors & Trims Distribution | 4824 |  | 0% | 4824
35 | PC SUM - Railings Supply | 74092 |  | 0% | 74092
36 | Millwork Install | 214860 |  | 0% | 214860
37 | Insulation & Foundation Treatment | 237151 |  | 0% | 237151 | 0 | 0% |  |  | 237151 | 100%
38 | Spray Foam insulation | 25000 |  | 0% | 25000 | 0 | 0% |  |  | 25000 | 100%
39 | Fire Caulking/Fire Spray | 171987 |  | 0% | 171987 | 0 | 0% |  |  | 171987 | 100%
40 | PC SUM - Fire Spray 4th Floor Corridors | 25000 |  | 0% | 25000
41 | PC SUM - Vinyl Decking & Aluminum Railings | 206697 |  | 0% | 206697 | 0 | 0% |  |  | 206697 | 100%
42 | Hardi-board & Lux Siding | 2178744 |  | 0% | 2178744 | 0 | 0% |  |  | 2178744 | 100%
43 | Bonding - Siding | 21787 |  | 0% | 21787
44 | PC SUM - SBS Roof | 1000977 |  | 0% | 1000977 | 0 | 0% |  |  | 1000977 | 100%
45 | PC SUM - Bonding - Roofing | 13863 |  | 0% | 13863
46 | Flashings / Caulking / Peel & Stick | 84692 |  | 0% | 84692 | 0 | 0% |  |  | 84692 | 100%
47 | FRP Panel | 13769 |  | 0% | 13769
48 | PC SUM - HMD/PSF/Finish Supply | 80347 |  | 0% | 80347 | 0 | 0% |  |  | 80347 | 100%
49 | HMD & PSF Install | 29780 |  | 0% | 29780
50 | PC SUM - Finish Hardware | 251500 |  | 0% | 251500
51 | PC SUM - Card Access System | 42600 |  | 0% | 42600 | 0 | 0% |  |  | 42600 | 100%
52 | PC SUM - Filter Access Door Supply | 20200 |  | 0% | 20200 | 0 | 0% |  |  | 20200 | 100%
53 | Filter Access Doors Install | 9474 |  | 0% | 9474
54 | PC SUM - Aluminum Doors and Windows | 315234 |  | 0% | 315234 | 0 | 0% |  |  | 315234 | 100%
55 | PC SUM - PVC Windows | 423691 |  | 0% | 423691 | 0 | 0% |  |  | 423691 | 100%
56 | PC SUM - Overhead Door | 9975 |  | 0% | 9975 | 0 | 0% |  |  | 9975 | 100%
57 | Parging | 26400 |  | 0% | 26400 | 0 | 0% |  |  | 26400 | 100%
58 | Structural steel stud/deck/insulation/vapour barrier/tape/texture | 7896670 |  | 0% | 7896670 | 0 | 0% |  |  | 7896670 | 100%
59 | PC SUM - Architectural Ceilings | 250000 |  | 0% | 250000 | 0 | 0% |  |  | 250000 | 100%
60 | Bonding - Steel Studs & Drywall | 70046 |  | 0% | 70046 | 0 | 0% |  |  | 70046 | 100%
61 | PC SUM - Flooring | 641495 |  | 0% | 641495 | 0 | 0% |  |  | 641495 | 100%
62 | PC SUM - Floor Patch | 20000 |  | 0% | 20000
63 | Bonding - Flooring | 7610 |  | 0% | 7610
64 | Painting | 359489 |  | 0% | 359489 | 0 | 0% |  |  | 359489 | 100%
65 | PC SUM - Wash. Partitions /Corner Guards Supply | 23952 |  | 0% | 23952 | 0 | 0% |  |  | 23952 | 100%
66 | Wash. Partitions / Corner Guards Install | 7622 |  | 0% | 7622
67 | PC SUM - Postal Services Supply | 10984 |  | 0% | 10984 | 0 | 0% |  |  | 10984 | 100%
68 | Postal Services Install | 2251 |  | 0% | 2251
69 | PC SUM - Washroom Accessories Supply | 29360 |  | 0% | 29360 | 0 | 0% |  |  | 29360 | 100%
70 | Washroom Accessories Install | 17810 |  | 0% | 17810
71 | Commercial Laundry Equipment | 23381 |  | 0% | 23381 | 0 | 0% |  |  | 23381 | 100%
72 | PC SUM - Appliances | 453662 |  | 0% | 453662 | 0 | 0% |  |  | 453662 | 100%
73 | PC SUM - Wire Shelving / Mirrors to suites | 35045 |  | 0% | 35045 | 0 | 0% |  |  | 35045 | 100%
74 | Elevators | 468102 |  | 0% | 468102 | 0 | 0% |  |  | 468102 | 100%
76 | Mechanical | 4568612 |  | 0% | 4568612 | 0 | 0% |  |  | 4568612 | 100%
77 | Bonding - Mechanical | 38515 |  | 0% | 38515
78 | Corridor Pressurization unites | 345400 |  | 0% | 345400 | 0 | 0% |  |  | 345400 | 100%
79 | Sprinklers | 306000 |  | 0% | 306000 | 0 | 0% |  |  | 306000 | 100%
80 | Electrical | 1919783 |  | 0% | 1919783 | 0 | 0% |  |  | 1919783 | 100%
81 | Bonding - Electrical | 24640 |  | 0% | 24640
82 | PC SUM - Electrical from demark to Property Line | 15000 |  | 0% | 15000
83 | PC Sum lighting Package | 152809 |  | 0% | 152809 | 0 | 0% |  |  | 152809 | 100%
85 | PC SUM - Fireplace | 25000 |  | 0% | 25000 | 0 | 0% |  |  | 25000 | 100%
| Building Construction Costs - Totals | 29554545 | 0 | 0% | 29554545 | 0 | 0% | 0 | 0 | 28611459 | 96.81%
Change Orders
|  |  |  | New Item | 0 | 0 | 0% |  |  | 0 | #DIV/0!
| Change Orders - Totals |  | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
Construction Totals
| General Conditions | 2610333 | 0 | 0% | 2610333 | 0 | 0% | 0 | 0 | 2610333 | 100%
| Sitework | 2523284 | 0 | 0% | 2523284 | 0 | 0% | 0 | 0 | 2284050 | 90.52%
| Building Construction Costs | 29554545 | 0 | 0% | 29554545 | 0 | 0% | 0 | 0 | 28611459 | 96.81%
| Project Overhead & Fee (6%) | 2081209 |  | 0% | 2081209 | 0 | 0% | 0 | 0 | 2081209 | 100%
| Construction Costs - Total | 36769371 | 0 | 0% | 36769371 | 0 | 0% | 0 | 0 | 36769371 | 100%
Direct Costs
| Temporary Utilities Consumption | 50000 |  | 0% | 50000 | 0 | 0% |  |  | 50000 | 100%
| Architectural Fees | 500000 |  | 0% | 500000 | 0 | 0% |  |  | 500000 | 100%
9 | Engineering - Mechanical/Electrical/Structural/Civil | 280725 |  | 0% | 280725 | 0 | 0% |  |  | 280725 | 100%
| Interior Design | 30000 |  | 0% | 30000 | 0 | 0% |  |  | 30000 | 100%
| Commercial Kitchen | 300000 |  | 0% | 300000 | 0 | 0% |  |  | 300000 | 100%
| Security and Fire Alarm | 49600 |  | 0% | 49600 | 0 | 0% |  |  | 49600 | 100%
| Furniture/Fixtures/Equipment/Blinds | 300000 |  | 0% | 300000 | 0 | 0% |  |  | 300000 | 100%
| Landscape Furniture | 75000 |  | 0% | 75000 | 0 | 0% |  |  | 75000 | 100%
| Building Signage | 50000 |  | 0% | 50000 | 0 | 0% |  |  | 50000 | 100%
| Foundation Permit | 40000 |  | 0% | 40000 | 0 | 0% |  |  | 40000 | 100%
4 | Sanitary Sewer Trunk Fund | 125846 |  | 0% | 125846 | 0 | 0% |  |  | 125846 | 100%
| Sanitary, Storm, Water Connection | 125000 |  | 0% | 125000 | 0 | 0% |  |  | 125000 | 100%
| Miscellaneous: Art, Site Trailer, etc. | 50000 |  | 0% | 50000 | 0 |  |  |  | 50000
| Direct Costs - Total | 1976171 | 0 | 0% | 1976171 | 0 | 0% | 0 | 0 | 1976171 | 100%
Soft Costs
Legal, Administration, Property Taxes, etc
| Re-Zoning Fee |  |  | 0% | 0 | 0 | 0% |  |  | 0 | #DIV/0!
2 | Development Permit | 9970 |  | 0% | 9970 | 0 | 0% |  |  | 9970 | 100%
5 | Building Permit Fee | 309850 |  | 0% | 309850 | 0 | 0% |  |  | 309850 | 100%
| BGN Municipal Upgrades | 161400 |  | 0% | 161400 | 0 | 0% |  |  | 161400 | 100%
| Developer Expenses | 142288 |  | 0% | 142288 | 0 | 0% |  |  | 142288 | 100%
| Cormode & Dickson Management Fee | 94947 |  | 0% | 94947 | 0 | 0% |  |  | 94947 | 100%
| Internal Management/Administration Costs | 300000 |  | 0% | 300000 | 0 | 0% |  |  | 300000 | 100%
| Legal | 25000 |  | 0% | 25000 | 0 | 0% |  |  | 25000 | 100%
| Quantity Surveyor | 45000 |  | 0% | 45000 | 0 | 0% |  |  | 45000 | 100%
| Property Taxes During Construction |  |  | 0% | 0 | 0 | 0% |  |  | 0 | #DIV/0!
| FCT Title Insurance | 10000 |  | 0% | 10000 | 0 | 0% |  |  | 10000 | 100%
| Financing Fees | [8 empty] | 0 | #DIV/0!
| Application Fee | 210000 |  | 0% | 210000 | 0 | 0% |  |  | 210000 | 100%
| Draw Fee | 6000 |  | 0% | 6000 | 0 | 0% |  |  | 6000 | 100%
| Appraisal | 14300 |  | 0% | 14300 | 0 | 0% |  |  | 14300 | 100%
| GST Self-Assessment | 975000 |  | 0% | 975000 | 0 | 0% |  |  | 975000 | 100%
| Soft Costs - Total | 2303755 | 0 | 0% | 2303755 | 0 | 0% | 0 | 0 | 2303755 | 100%
Principal Cost Summary
| Construction | 36769371 | 0 | 0% | 36769371 | 0 | 0% | 0 | 0 | 36769371 | 1
| Direct Costs | 1976171 | 0 | 0% | 1976171 | 0 | 0% | 0 | 0 | 1976171 | 1
| Land Cost - not included | 7150000 | 0 | 0% | 7150000 | 0 | 0% | 0 | 0 | 7150000 | 0
| Soft Costs | 2303755 | 0 | 0% | 2303755 | 0 | 0% | 0 | 0 | 2303755 | 1
| Sub-Totals | 48199297 | 0 | 0% | 48199297 | 0 | 0% | 0 | 0 | 48199297 | 100%
| Contingencies | 2052464.85 | 0 | 0% | 2052464.85 | 0 | 0% | 0 |  | 2052464.85
| Interest | 2391444 |  | 0% | 2391444 | 0 | 0% |  |  | 2391444
| Project Costs | 52643205.85 | 0 | 0% | 52643205.85 | 0 | 0% | 0 | 0 | 52643205.85 | 100%
| Bonding Costs in Toto | 212606