## Sheet1
Quality Improvement Plan
Emmanuel Home
Quality Improvement Plan January 2022- January 2025
Quality Dimensions | Goals | Objectives | Performance Measures | Current Performance | Target | Activities | Timeframe | Resources | Responsibility
Staff Mental Health & Wellness | Bring increased awareness and communication on this. Improve scoring on Employee Wellness Survey | Increase overall communication and focus on Mental Health Awareness | Employee Wellness Survey | 6/36 are not likely to recommend friends or family to work here | Lessen to 2 people | Employee Participation Challenge Groups – potlucks, games, interacting with residents, BBQ’s etc | Initiated January 2023 | https://mentalhealthcommission.ca/ | Dept Managers
|  | Obtain normalcy to discussing this topic | Reduced Sick Time | 19/36 people do not feel that conversations about mental health and stress are normal at Emmanuel Home | Increase overall survey participation | Mental Health Check-ins |  | CCSA | Senior Leadership
|  |  | Overall Positive Employee Culture |  | Lessen by 5-10 people |  |  | Employee Wellness Survey
WorkLife Pulse Tool
Med Errors | Reduce Medication Errors by 10% | Continual education on med admin | Tracking |  | Increase confidence of healthcare staff in med admin. | Quarterly Education | Assess every 6 months. | https://connection.albertahealthservices.ca/ | DOC
[5 empty] | Engage healthcare employee in a positive supportive environment that brings accountability and championing of proper medication administration. |  |  |  | Healthcare Dept.
| Establish regular reporting to Leadership & Board | Create process for delivery of reporting schedule | Reduction of errors |  |  | Lead LPN champion | Reduction by 10% each year. | CLPNA
[6 empty] | HCA champion |  | AHS
Complaints Resolution | Establish routine reporting system and tracking for complaints | Capture overall resolution follow-up and satisfaction rating | Satisfaction Surveys | No formal process in place for complaints resolution. | Enagae employees in completing process for documentaiton of complaints and followup. | Education | Initiate process by February 2023 | Accreditation | Board
Actions are completed but minimal to no documnetation performed
|  |  | Annual Review |  |  | Process implementation |  | CCHSS | Senior Leadership
Dept Managers
Employees
Quality Dimensions | Goals | Objectives | Performance Measures | Current Performance | Target | Activities | Timeframe | Resources | Responsibility
Source: Adapted from the Collaborative for Excellence in Healthcare Quality, A Guide to Developing and Assessing a Quality Plan for Healthcare Organizations (2012)